## Anomaly Resolution Tracker
Monitri BaaS Platform — Anomaly Resolution Tracker ¦ FIDP-2025-001 ¦ Anumeha Princy, PMP® — Operations PM
Project ID: FIDP-2025-001 ¦ Data Period: January–May 2025 ¦ Q7: 7 High/Critical Escalated Anomalies
Anomaly_ID | Detected_Date | Client_ID | Region | Anomaly_Type | Severity | Action_Taken | Assigned_To | Resolution_Status | Resolution_Date | Resolution_Detail | Resolution_Reference
ANO-0015 | 2025-02-06 | CLT-0259 | United States | Volume Drop | High | Reviewed with VP Engineering — confirmed resolution ownership and timeline. Added to weekly ops status dashboard. Pattern documented — linked to CI/CD deployment failure. | VP Engineering | Resolved | 2025-02-06 | Root cause: deployment issue. VP Engineering investigated and resolved same day. Volumes restored within SLA window. | COO_Weekly_Status_Report_Mar17 — Action Item #4 confirms 7 escalated anomalies tracked by Ops PM + VP Eng
ANO-0018 | 2025-02-12 | CLT-0202 | United States | Volume Drop | Critical | Reviewed with VP Engineering — confirmed resolution ownership and timeline. Coordinated proactive client notification via Head of Client Success. Added to weekly ops status dashboard. | VP Engineering | Resolved | 2025-02-12 | Critical severity. Root cause: deployment issue. Proactive client notification issued by Head of Client Success. Resolved same day. | COO_Weekly_Status_Report_Mar17 — Action Item #4 confirms tracking of all 7 escalated High/Critical anomalies
ANO-0030 | 2025-03-10 | CLT-0338 | Germany | Volume Drop | Critical | Reviewed with VP Engineering — confirmed resolution ownership. Coordinated proactive client notification. Flagged Germany as European regional risk — cross-referenced with SLA breach data. Added to weekly ops dashboard. | VP Engineering | Resolved | 2025-03-10 | Critical severity. Germany client — European regional risk flagged. Cross-referenced with SLA breach data. Infrastructure review recommended. | COO_Weekly_Status_Report_Mar17 — Section 5 flags European regional risk; Action Item #4 confirms anomaly tracking
ANO-0034 | 2025-03-13 | CLT-0283 | United States | Volume Spike | Critical | Reviewed with VP Engineering — confirmed resolution ownership. Coordinated proactive client notification via Head of Client Success. Pattern documented — all escalations rooted in deployment issues linked to CI/CD failure data. | VP Engineering | Resolved | 2025-03-13 | Critical severity. Highest volume spike in dataset. Proactive client notification issued. Resolved same day. | COO_Weekly_Status_Report_Mar17 — Action Item #4 confirms all 7 escalated anomalies assigned resolution owners
ANO-0042 | 2025-03-24 | CLT-0121 | United Kingdom | Volume Spike | High | Reviewed with VP Engineering — confirmed resolution ownership and timeline. Added resolution tracking to weekly ops dashboard. Systemic observation escalated — all escalated anomalies linked to CI/CD pipeline failures. | VP Engineering | Resolved | 2025-03-24 | High severity. Root cause linked to CI/CD deployment pipeline failure pattern. Resolution confirmed by VP Engineering. | Monitri_Jira_DEP0109_Incident_Lifecycle_v3 — documents systemic CI/CD deployment failure pattern escalated to VP Engineering
ANO-0062 | 2025-05-06 | CLT-0221 | United States | Volume Spike | High | Reviewed with VP Engineering — confirmed resolution ownership. Stripe API mismatch confirmed as recurring systemic root cause — fourth occurrence across 5 months. Escalated for permanent architectural fix not patch. | VP Engineering | Resolved | 2025-05-06 | High severity. Root cause: Stripe API version mismatch — recurring systemic issue. Permanent fix escalated to VP Engineering. | Monitri_Jira_DEP0104_Incident_Lifecycle — Stripe API mismatch confirmed as recurring root cause; VP Engineering escalation backed
ANO-0067 | 2025-05-14 | CLT-0103 | Netherlands | Failed Transaction Surge | High | Reviewed with VP Engineering — confirmed resolution ownership and timeline. Netherlands flagged as European regional risk. Failed transaction surge linked to deployment pipeline issue — cross-referenced with CI/CD failure data. | VP Engineering | Resolved | 2025-05-14 | High severity. Netherlands client — European regional risk. Failed transaction surge linked to deployment pipeline. Resolved by VP Engineering. | Monitri_Jira_Jumio_Vendor_Lifecycle — European regional risk (Netherlands) documented; cross-referenced with vendor and deployment failure patterns