## Communication Tracker
Monitri BaaS Platform — Communication Tracker ¦ FIDP-2025-001 ¦ Anumeha Princy, PMP® — Operations PM
Project ID: FIDP-2025-001 ¦ Data Period: January–May 2025 ¦ All communications owned by Operations PM
Comm_ID | Date | Communication_Type | Sent_By | Sent_To | Related_Incident | Channel | Purpose | Outcome | Proof_Reference
COMM-001 | 2025-02-28 | Vendor Alert | Anumeha Princy, PMP® — Ops PM | Vendor Management Lead | VND-003-FEB | Email | First Jumio SLA breach alert — raise awareness, initiate monitoring | Vendor Management Lead notified. Jumio performance monitoring initiated. | Monitri_Jira_Jumio_Vendor_Lifecycle — Comment 1
COMM-002 | 2025-03-11 | P2 Escalation Email | Anumeha Princy, PMP® — Ops PM | VP Engineering | DEP-0104 | Email | Escalate P2 production failure — SSL certificate validation failure, 39 clients affected | VP Engineering acknowledged. Root cause confirmed. Resolution initiated. | Monitri_VP_Engineering_Email_DEP0104 — Email 1 (amber header)
COMM-003 | 2025-03-11 | Client Outreach Email | Anumeha Princy, PMP® — Ops PM | 39 affected clients — via Head of Client Success | DEP-0104 | Email | Proactive notification to all 39 clients before any client-initiated escalation | All 39 clients notified proactively. Zero client-initiated escalations recorded. | Monitri_Client_Outreach_Email_DEP0104.pdf
COMM-004 | 2025-03-11 | VP Engineering Resolution Confirmation | VP Engineering | Anumeha Princy, PMP® — Ops PM | DEP-0104 | Email | Confirm SSL certificate renewed, service restored, pipeline updated | DEP-0104 resolved. Pipeline updated to include automatic certificate validation. | Monitri_VP_Engineering_Email_DEP0104 — Email 3 (green header)
COMM-005 | 2025-03-15 | COO Vendor Escalation | Anumeha Princy, PMP® — Ops PM | COO | VND-003-MAR | Email | Escalate Jumio 2-month SLA breach pattern — request COO awareness and approval for next steps | COO acknowledged. Formal vendor review request approved. Contingency assessment initiated. | Monitri_Jumio_Vendor_Proof_Documents — Document 1 (COO escalation email)
COMM-006 | 2025-03-15 | Formal Vendor Review Request | Anumeha Princy, PMP® — Ops PM | Jumio Account Team | VND-003-MAR | Email | Formal SLA breach notification — request RCA, remediation plan, and escalation contact | Jumio acknowledged in April 2025. RCA and remediation plan provided. | Monitri_Jumio_Vendor_Proof_Documents — Document 2 (formal review letter)
COMM-007 | 2025-03-16 | P1 Escalation Email | Anumeha Princy, PMP® — Ops PM | VP Engineering | DEP-0109 | Email | Escalate P1 production failure — network timeout, 58 clients affected, highest impact YTD | VP Engineering escalated immediately. Root cause patched same day. | Monitri_VP_Engineering_Email_DEP0109 — Email 1 (red header)
COMM-008 | 2025-03-16 | Client Outreach Email | Anumeha Princy, PMP® — Ops PM | 58 affected clients — via Head of Client Success | DEP-0109 | Email | Proactive notification to all 58 clients before any client-initiated escalation | All 58 clients notified proactively. Zero client-initiated escalations recorded. | Monitri_Client_Outreach_Email_DEP0109_v2.pdf
COMM-009 | 2025-03-16 | VP Engineering Resolution Confirmation | VP Engineering | Anumeha Princy, PMP® — Ops PM | DEP-0109 | Email | Confirm network timeout patched, service restored, API versioning protocol recommended | DEP-0109 resolved. Permanent API versioning protocol with Stripe recommended. | Monitri_VP_Engineering_Email_DEP0109 — Email 2 (green header)
COMM-010 | 2025-03-17 | COO Weekly Status Report | Anumeha Princy, PMP® — Ops PM | COO + VP Engineering + Head of Client Success | Multiple | Email + Dashboard | Weekly platform health briefing — DEP-0109, DEP-0104, Jumio, 7 escalated anomalies | COO briefed. Action items assigned. Red status on 3 of 4 platform metrics documented. | FIDP_2025_COO_Weekly_Status_Report_Mar17.pdf — C001 communication
COMM-011 | 2025-04-15 | Compliance Team Risk Assessment | Anumeha Princy, PMP® — Ops PM | Compliance Team | VND-003-APR | Email | Request regulatory risk assessment — Jumio KYC degradation impact on European clients under GDPR and PSD2 | Compliance Team engaged. Regulatory exposure assessed. Backup vendor criteria informed. | Monitri_Jumio_Vendor_Proof_Documents — Document 3 (Compliance Team email)
COMM-012 | 2025-04-20 | Jumio Response — RCA and Remediation Plan | Jumio Account Team | Anumeha Princy, PMP® — Ops PM | VND-003-APR | Email | Jumio formally acknowledges SLA breach — provides RCA, remediation plan, and preventive measures | RCA received. Remediation plan accepted. Performance watch initiated. | Monitri_Jumio_Response_Email.pdf
COMM-013 | 2025-05-31 | 90-Day Performance Watch Letter | Anumeha Princy, PMP® — Ops PM | Jumio Account Team | VND-003-MAY | Email + PDF | Formally place Jumio on 90-day performance watch — June through August 2025 | Jumio notified. Watch terms communicated. Remediation plan due June 15, 2025. | Monitri_Jumio_Vendor_Proof_Documents — Document 4 (90-day watch letter)
COMM-014 | 2025-05-31 | VP Engineering Stripe Briefing | Anumeha Princy, PMP® — Ops PM | VP Engineering | STRIPE-DUAL | Email + PDF | Brief VP Engineering on Stripe dual systemic risk — vendor SLA breach AND CI/CD root cause | Permanent API versioning protocol requested. Engineering backlog reprioritization initiated. | Monitri_VP_Engineering_Stripe_Briefing.pdf
COMM-015 | 2025-09-10 | Jumio Termination Letter | Anumeha Princy, PMP® — Ops PM | Jumio Account Team | VND-003-TERMINATION | Email + PDF | Formal termination notice — 60-day notice period. Jumio failed 2 of 3 watch months. | Jumio acknowledged. 60-day notice period commenced. Offboarding initiated. | Monitri_Jumio_Termination_Documents.pdf — Termination letter
COMM-016 | 2025-09-10 | Client Notification — Jumio Termination | Anumeha Princy, PMP® — Ops PM | Affected clients — via Head of Client Success | VND-003-TERMINATION | Email | Notify clients of KYC vendor transition — maintain confidence, confirm continuity of service | Clients notified proactively. Service continuity confirmed. Zero client-initiated escalations. | Monitri_Client_Notification_Email — Jumio termination client outreach