## Escalation Log
Monitri BaaS Platform — Escalation Log ¦ FIDP-2025-001 ¦ Anumeha Princy, PMP® — Operations PM
Project ID: FIDP-2025-001 ¦ Data Period: January–May 2025 ¦ Simulated BaaS Environment
Escalation_ID | Date | Incident_ID | Escalation_Type | Escalated_By | Escalated_To | Priority | Response_Time | Outcome | Proof_Reference
ESC-001 | 2025-02-28 | VND-003-FEB | Vendor SLA Breach — First Occurrence | Anumeha Princy, PMP® — Ops PM | Vendor Management Lead | Medium | Same day | Alert raised. Jumio performance monitoring initiated. Recurrence watch active. | Monitri_Jira_Jumio_Vendor_Lifecycle — Comment 1 ¦ vendor_performance dataset VND-003 Feb-2025
ESC-002 | 2025-03-15 | VND-003-MAR | Vendor SLA Breach — 2-Month Pattern | Anumeha Princy, PMP® — Ops PM | COO | High | Same day | COO acknowledged. Formal vendor performance review submitted to Jumio. Contingency assessment initiated. | Monitri_Jumio_Vendor_Proof_Documents — Doc 1 (COO email) + Doc 2 (formal review letter)
ESC-003 | 2025-03-11 | DEP-0104 | P2 CI/CD Production Failure — SSL Certificate | Anumeha Princy, PMP® — Ops PM | VP Engineering | High | 15 minutes — same day resolution | VP Engineering acknowledged. SSL renewed and redeployed. 39 clients restored. Zero client escalations. | Monitri_VP_Engineering_Email_DEP0104 — Email 1 + Email 2 + Email 3
ESC-004 | 2025-03-16 | DEP-0109 | P1 CI/CD Production Failure — Network Timeout | Anumeha Princy, PMP® — Ops PM | VP Engineering | Critical | 15 minutes — same day resolution | Root cause patched same day. 58 clients restored. Zero client escalations. 92% detection improvement. | Monitri_VP_Engineering_Email_DEP0109 — Email 1 (P1 escalation) + Email 2 (resolution)
ESC-005 | 2025-04-15 | VND-003-APR | Vendor SLA Breach — 3rd Month + Regulatory Risk | Anumeha Princy, PMP® — Ops PM | Compliance Team | High | Same day | Compliance Team engaged on GDPR and PSD2 risk for European clients. Backup KYC assessment initiated. | Monitri_Jumio_Vendor_Proof_Documents — Doc 3 (Compliance Team email)
ESC-006 | 2025-04-20 | VND-003-APR | Vendor SLA Breach — Formal Escalation Call | Anumeha Princy, PMP® — Ops PM | Jumio Account Team | High | Jumio responded April 2025 | Jumio acknowledged breach. RCA provided. Remediation plan submitted with timeline. | Monitri_Jumio_Response_Email — Jumio formal response with RCA and remediation plan
ESC-007 | 2025-05-31 | VND-003-MAY | Vendor SLA Breach — 90-Day Watch Initiated | Anumeha Princy, PMP® — Ops PM | Jumio Account Team | High | Immediate — formal letter issued | Jumio placed on 90-day performance watch June–August 2025. Remediation plan due June 15. | Monitri_Jumio_Vendor_Proof_Documents — Doc 4 (90-day watch letter)
ESC-008 | 2025-03-17 | ANO-BATCH-01 | 7 Escalated High/Critical Anomalies — Batch | Anumeha Princy, PMP® — Ops PM | VP Engineering | High | Resolution target March 20, 2025 | All 7 anomalies assigned owners and timelines. Critical clients notified. Pattern linked to CI/CD failures. | COO_Weekly_Status_Report_Mar17 — Action Item #4 ¦ Monitri_Anomaly_Resolution_Tracker.xlsx
ESC-009 | 2025-05-31 | STRIPE-DUAL | Stripe Dual Risk — Vendor SLA + CI/CD Root Cause | Anumeha Princy, PMP® — Ops PM | VP Engineering + COO | High | VP Engineering briefing issued May 31 | Stripe documented as dual risk. Permanent API versioning protocol requested. | Monitri_VP_Engineering_Stripe_Briefing.pdf ¦ Monitri_SLA_Recommendation_Memo.pdf
ESC-010 | 2025-09-10 | VND-003-TERMINATION | Jumio Termination — Watch Period Failed | Anumeha Princy, PMP® — Ops PM | COO | High | COO approved same day | Jumio terminated. 60-day notice issued. Offboarded November 2025. CHG006 raised. | Monitri_Jira_Jumio_Vendor_Lifecycle — Comments 4-6 ¦ COO Termination Memo ¦ CHG006